## Project Planner
Junior Project Planner 30 - Weeks
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 7 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Team Activities | bar: PERIODS 1 to PERIODS 20
| Initial Parts Order | 0 | 0 | 0 | 0 | 0%
| Microprocessor Final Testing | 0 | 0 | 0 | 0 | 0%
| Camera Final Testing | 0 | 0 | 0 | 0 | 0%
| Activity 05 | 0 | 0 | 0 | 0 | 0%
| Activity 06 | 0 | 0 | 0 | 0 | 0%
| Activity 07 | 0 | 0 | 0 | 0 | 0%
| Activity 08 | 0 | 0 | 0 | 0 | 0%
| Activity 09 | 0 | 0 | 0 | 0 | 0%
| Activity 10 | 0 | 0 | 0 | 0 | 0%
Drew (Microcontroller, Power Supply, Proximity Sensor, Camera, LED Notification) | bar: PERIODS 1 to PERIODS 20
| Initial Parts Order | 4 | 1 | 4 | 1 | 100%
| Initial Parts Testing (PIC32) | 5 | 1 | 5 | 1 | 100%
| Initial Parts Testing (Power Supply) | 7 | 1 | 0 | 0 | 0%
| Initial Parts Testing (Proximity Sensor) | 7 | 1 | 7 | 0 | 0%
| Initial Parts Testing (Camera) | 10 | 1 | 0 | 0 | 0%
| Initial Parts Testing (LED's) | 7 | 1 | 7 | 1 | 100%
| Microproccessor Phase 1 | 5 | 1 | 6 | 1 | 100%
| Microproccessor Phase 2 | 0 | 0 | 0 | 0 | 0%
| Power Supply Phase 1 | 6 | 1 | 0 | 0 | 0%
| Power Supply Phase 2 | 6 | 1 | 0 | 0 | 0%
| Power Supply Phase 3 | 12 | 4 | 0 | 0 | 0%
| Power Supply Final Testing | 20 | 4 | 0 | 0 | 0%
| Proximity Sensor Phase 1 | 14 | 0 | 0 | 0 | 0%
| Proximity Sensor Final Testing | 20 | 0 | 0 | 0 | 0%
| Camera Phase 1 | 16 | 2 | 0 | 0 | 0%
| Camera Phase 2 | 18 | 3 | 0 | 0 | 0%
| LED Phase 1 | 7 | 1 | 0 | 0 | 0%
| LED Final Testing | 20 | 1 | 0 | 0 | 0%
Chad (Motor Operations, Temerature Sensor, Speaker, Proximity Sensor, Blinds) | bar: PERIODS 1 to PERIODS 20
| Initial Parts Order | 4 | 1 | 4 | 1 | 100%
| Gas Sensor Initial Test | 10 | 1 | 0 | 0 | 0%
| Gas Sensor Phase 1 | 10 | 1 | 0 | 0 | 0%
| Gas Sensor Final Testing | 15 | 1 | 0 | 0 | 0%
| Stepper Motor Initial Test | 9 | 1 | 0 | 0 | 0%
| Stepper Motor Phase 1 | 10 | 1 | 0 | 0 | 0%
| Stepper Motor Phase 2 | 11 | 1 | 0 | 0 | 0%
| Stepper Motor Final Test | 12 | 2 | 0 | 0 | 0%
| Temperature Initial Test | 10 | 1 | 0 | 0 | 0%
| Temperature Phase 1 | 11 | 1 | 0 | 0 | 0%
| Temperature Final Test | 12 | 1 | 0 | 0 | 0%
| Speaker Initial Test | 9 | 1 | 0 | 0 | 0%
| Speaker Phase 1 | 10 | 1 | 0 | 0 | 0%
| Speaker Final Test | 11 | 1 | 0 | 0 | 0%
Michael (Wi-Fi, Application) | bar: PERIODS 1 to PERIODS 20
| Initial Parts Order | 4 | 1 | 4 | 1 | 100%
| Initial Parts Testing (Wifi Module MCU) | 8 | 2 | 0 | 0 | 0%
| Initial Parts Testing (Database) | 7 | 1 | 7 | 1 | 100%
| Initial Parts Testig (Web Server) | 8 | 1 | 7 | 2 | 100%
| Initial Parts Testing (Router) | 8 | 1 | 8 | 1 | 100%
| Initial Parts Testing (Software) | 12 | 3 | 0 | 0 | 0%
| Initial Project Plan Database Diagrams | 6 | 1 | 6 | 0 | 0%
| Initial Project Plan Software Diagrams | 6 | 1 | 6 | 0 | 0%
| Initial Project Plan Wi-Fi MCU State Machine Diagram | 6 | 1 | 6 | 0 | 0%
| Wi-Fi MCU Code(Tier 4) | 7 | 3 | 7 | 0 | 0%
| Front-End GUI Code(Tier 1) | 7 | 3 | 7 | 0 | 0%
| Web Service Code (Tier 2) | 7 | 3 | 7 | 0 | 0%
| Datatbase Code (Tier 3) | 7 | 3 | 7 | 0 | 0%
| MCU Intergration | 14 | 2 | 0 | 0 | 0%
| Fall Term Project Presentation | 7 | 1 | 7 | 1 | 0%
Schedule Notes (Term 1) | bar: PERIODS 1 to PERIODS 4
10/31/2019 - Nothing to change. Will update during next meeting 10.2.2019
11/6/2019 - No other updates from team. Chad and Drew will give updates next team teaming Wednesday.
11/13/2019 - No updates from team. Doing Preliminary Schedule and will update First week of next term.